## Launch Plan
YOW paid-launch plan
One owner task per weekday · provisional launch 30 November 2026 · weekends protected
Tasks | 46 |  | How to use
Done | 0 |  | Update only Status and Notes. Start with the task for today. If a hard gate fails, move launch by one week rather than compressing the two-week marketing runway. Closing public Beta enrollment never revokes existing testers or deletes their data.
Remaining | 46
Blocked | 0
Progress | 0%
Date | Week | Phase | Your task | Engineering / QA outcome | Hard gate | Status | Notes
2026-09-28 12:00 | Week 1 | Release baseline | Approve the calendar and reserve weekday review blocks through 30 November. | Freeze launch scope and classify every remaining item as launch-blocking, verification-only, or post-launch. | Yes | Not started
2026-09-29 12:00 | Week 1 | Release baseline | Review the short release-baseline report and decide only if a true scope conflict is surfaced. | Make npm run qa green, reconcile the Vercel route test, and review current uncommitted work. | Yes | Not started
2026-09-30 12:00 | Week 1 | Release baseline | Run a 30-minute sign-in, project, writing, and export smoke test. | Commit a clean baseline and record test, build, bundle, and warning results. | Yes | Not started
2026-10-01 12:00 | Week 1 | Release baseline | Confirm the six launch project types and excluded promises still match the product you intend to sell. | Reconcile stale roadmap and marketing contradictions, especially desktop and coming-soon language. | Yes | Not started
2026-10-02 12:00 | Week 1 | Release baseline | Review the Week 1 status and approve the ordered blocker queue. | Cut the first launch candidate only if the baseline is green. | Yes | Not started
2026-10-05 12:00 | Week 2 | Data safety | Provide the production Supabase session or access needed for the guided migration check. | Deploy and verify scene concurrency and Security Definer hardening migrations; rerun database advisors. | Yes | Not started
2026-10-06 12:00 | Week 2 | Data safety | Perform the guided two-tab same-scene edit test with the designated test account. | Verify leases, stale-revision rejection, conflict-copy review, recovery, and no silent overwrite. | Yes | Not started
2026-10-07 12:00 | Week 2 | Data safety | Perform the guided two-account isolation and account-switch test. | Verify auth isolation, local ownership, AI-key isolation, entitlement tampering rejection, and recovery. | Yes | Not started
2026-10-08 12:00 | Week 2 | Data safety | Approve or defer the optional git-history rewrite after reviewing the auth-log result. | Migrate the two missing production function definitions and review historical auth logs. | No | Not started
2026-10-09 12:00 | Week 2 | Data safety | Sign off the plain-English data-safety evidence packet. | Close the week only if migrations, two-tab, two-account, destructive actions, and rollback evidence are clean. | Yes | Not started
2026-10-12 12:00 | Week 3 | Cloud and exports | Test a real media upload, replacement, and deletion while watching the Storage figure. | Verify private-media RLS, cleanup, quota accounting, and signed rendering and export. | Yes | Not started
2026-10-13 12:00 | Week 3 | Cloud and exports | Run one guided full-account export and open representative ZIP, DOCX, PDF, and World Bible outputs. | Verify completeness, readable documents, PDF privacy, and restorable ZIP ownership. | Yes | Not started
2026-10-14 12:00 | Week 3 | Cloud and exports | Run guided import-as-new, import-into-existing, and second-account collision checks. | Verify ID remapping, rollback, double-import behavior, and no cross-account or partial-write failure. | Yes | Not started
2026-10-15 12:00 | Week 3 | Cloud and exports | Review the customer warning sequence for cloud expiry and inactive Free accounts. | Complete and test notices, Export All, grace, archive or delete policy, and cloud-write shutdown. | Yes | Not started
2026-10-16 12:00 | Week 3 | Cloud and exports | Approve the final cloud-expiry wording and evidence. | Close export ownership and storage-limit gates or move the launch target by one week. | Yes | Not started
2026-10-19 12:00 | Week 4 | Desktop Mac | Install the current macOS build on a clean or test Mac using only the written instructions. | Expose and verify the full desktop project workspace, auth, library, and editing. | Yes | Not started
2026-10-20 12:00 | Week 4 | Desktop Mac | Test writing, quit and reopen, force-quit recovery, snapshot, restore, and vault relocation. | Verify SQLite durability, integrity, WAL cleanup, folder warnings, and no data loss. | Yes | Not started
2026-10-21 12:00 | Week 4 | Desktop Mac | Test native ZIP, DOCX, PDF, and map PNG saves from the packaged Mac app. | Verify native dialogs, cancellation and errors, file contents, and updater packaging. | Yes | Not started
2026-10-22 12:00 | Week 4 | Desktop Mac | Run the guided Local Mode, lapse, web edit, renewal, and merge-conflict scenario. | Verify no cloud writes while lapsed, cold-start resume, retries, conflicts, and automatic sync restoration. | Yes | Not started
2026-10-23 12:00 | Week 4 | Desktop Mac | Approve Mac install and disclosure instructions after a clean-machine pass. | Produce versioned Mac artifacts, hashes, provenance, updater metadata, and a desktop report. | Yes | Not started
2026-10-26 12:00 | Week 5 | Desktop and project types | Arrange or perform the clean Windows install using the written SmartScreen steps. | Verify Windows install, WebView2, workspace, exports, updater, upgrade, and uninstall. | Yes | Not started
2026-10-27 12:00 | Week 5 | Desktop and project types | Confirm the download page shows correct files and unsigned-app disclosure to an entitled account. | Configure final download URLs and verify server-side entitlement gating. | Yes | Not started
2026-10-28 12:00 | Week 5 | Desktop and project types | Test Novella and Short Story create, write, default-sections, and export flows. | Close type-specific structure, template, navigation, persistence, and export checks. | Yes | Not started
2026-10-29 12:00 | Week 5 | Desktop and project types | Test D&D and TTRPG prep and recap, Character Builder, map sections, and export. | Close campaign persistence, language, AI context, and public-copy checks. | Yes | Not started
2026-10-30 12:00 | Week 5 | Desktop and project types | Test Novel and Comic workflows and approve the six-type evidence matrix. | Close live-Supabase and realistic-load checks across all six project types. | Yes | Not started
2026-11-02 12:00 | Week 6 | Product acceptance | Test the rebuilt Map Builder using the owner acceptance checklist. | Close creation, editing, layers, interaction, persistence, responsive, and export checks. | Yes | Not started
2026-11-03 12:00 | Week 6 | Product acceptance | Perform one realistic large-project session across every core workspace. | Record timings, resolve release-blocking lag, and decide the very-large-single-scene limit. | Yes | Not started
2026-11-04 12:00 | Week 6 | Product acceptance | Test each AI provider you intend to advertise; remove any provider you cannot verify. | Verify proxy auth, secrets, streaming, errors, context, disclosures, and persistence. | Yes | Not started
2026-11-05 12:00 | Week 6 | Product acceptance | Perform the guided phone, tablet, desktop, and accessibility pass. | Close responsive, real-iPhone, keyboard, focus, screen-reader, contrast, and theme checks. | Yes | Not started
2026-11-06 12:00 | Week 6 | Product acceptance | Approve the feature-completeness report or remove an unready promise from launch. | Close remaining worldbuilding, series, focused-writing, schedule, and AI-import gaps. | Yes | Not started
2026-11-09 12:00 | Week 7 | Legal and release candidate | Read Pricing, FAQ, Terms, Privacy, cancellation, storage, Local Mode, Founder, AI, and export copy as a customer. | Deliver one reconciled legal and promise packet with no behavior-copy contradictions. | Yes | Not started
2026-11-10 12:00 | Week 7 | Legal and release candidate | Approve final copy and business identity and contact details. | Freeze legal and marketing copy and verify every public claim. | Yes | Not started
2026-11-11 12:00 | Week 7 | Legal and release candidate | Work through the guided Stripe test-mode checklist one dashboard step at a time. | Verify plans, renewal, failure, replay, refunds, disputes, and Founder allocation. | Yes | Not started
2026-11-12 12:00 | Week 7 | Legal and release candidate | Approve beta-graduation email, launch announcement, pricing message, screenshots, and support template. | Prepare reversible Beta closure and tester migration scripts without running them. | Yes | Not started
2026-11-13 12:00 | Week 7 | Legal and release candidate | Hold the formal go or no-go review and say go only if every hard gate has evidence. | Freeze Release Candidate 1. A no-go moves later dates by one week without shortening the runway. | Yes | Not started
2026-11-16 12:00 | Week 8 | Marketing runway 1 | If go, approve closing new Beta enrollment and removing Beta from public plan choices. | Close new Beta grants and public enrollment while preserving existing tester access and exports. | Yes | Not started
2026-11-17 12:00 | Week 8 | Marketing runway 1 | Email existing Beta testers with launch timing, retained access, notice path, and backup steps. | Verify delivery, segmentation, support routing, and no entitlement revocation. | Yes | Not started
2026-11-18 12:00 | Week 8 | Marketing runway 1 | Publish the 30 November launch announcement and updated marketing pages. | Deploy launch-date marketing with checkout disabled; verify SEO, sitemap, analytics, and links. | Yes | Not started
2026-11-19 12:00 | Week 8 | Marketing runway 1 | Test the signed-out visitor journey on phone and desktop. | Fix only launch-blocking copy, navigation, or signup problems. | Yes | Not started
2026-11-20 12:00 | Week 8 | Marketing runway 1 | Review interest, tester replies, support load, and analytics; approve copy-only corrections. | Produce the first marketing-runway report without expanding product scope. | No | Not started
2026-11-23 12:00 | Week 9 | Marketing runway 2 | Publish the main use-case story and demonstrate one complete writer workflow. | Run Release Candidate 2 regression and production header, CSP, and analytics checks. | Yes | Not started
2026-11-24 12:00 | Week 9 | Marketing runway 2 | Publish the ownership, export, Local Mode, and desktop message. | Recheck artifacts, hashes, entitlement gating, backup and restore, and expiry copy. | Yes | Not started
2026-11-25 12:00 | Week 9 | Marketing runway 2 | Publish project-type examples and confirm all six are described honestly. | Rerun the six-type smoke matrix and marketing-promise tests. | Yes | Not started
2026-11-26 12:00 | Week 9 | Marketing runway 2 | Review the support runbook, refunds, cancellation, incident contacts, and rollback triggers. | Rehearse rollback, checkout disable, database backup, monitoring, and escalation. | Yes | Not started
2026-11-27 12:00 | Week 9 | Marketing runway 2 | Perform the final guided purchase rehearsal and sign the launch checklist. | Review live Stripe configuration and verify checkout in preview; keep production checkout off. | Yes | Not started
2026-11-30 12:00 | Week 10 | Launch | Approve the production checkout switch, announce launch, and monitor transactions and support. | Back up, deploy, enable checkout, migrate existing Beta accounts into the 30-day notice path, smoke-test, and keep rollback ready. | Yes | Not started

## Calendar
YOW launch calendar
Owner tasks only · engineering outcomes remain in the Launch Plan tab
Week 1 · 2026-09-28 to 2026-10-02 · Release baseline
Mon 28 Sept | Tue 29 Sept | Wed 30 Sept | Thu 1 Oct | Fri 2 Oct
Approve the calendar and reserve weekday review blocks through 30 November. | Review the short release-baseline report and decide only if a true scope conflict is surfaced. | Run a 30-minute sign-in, project, writing, and export smoke test. | Confirm the six launch project types and excluded promises still match the product you intend to sell. | Review the Week 1 status and approve the ordered blocker queue.
Week 2 · 2026-10-05 to 2026-10-09 · Data safety
Mon 5 Oct | Tue 6 Oct | Wed 7 Oct | Thu 8 Oct | Fri 9 Oct
Provide the production Supabase session or access needed for the guided migration check. | Perform the guided two-tab same-scene edit test with the designated test account. | Perform the guided two-account isolation and account-switch test. | Approve or defer the optional git-history rewrite after reviewing the auth-log result. | Sign off the plain-English data-safety evidence packet.
Week 3 · 2026-10-12 to 2026-10-16 · Cloud and exports
Mon 12 Oct | Tue 13 Oct | Wed 14 Oct | Thu 15 Oct | Fri 16 Oct
Test a real media upload, replacement, and deletion while watching the Storage figure. | Run one guided full-account export and open representative ZIP, DOCX, PDF, and World Bible outputs. | Run guided import-as-new, import-into-existing, and second-account collision checks. | Review the customer warning sequence for cloud expiry and inactive Free accounts. | Approve the final cloud-expiry wording and evidence.
Week 4 · 2026-10-19 to 2026-10-23 · Desktop Mac
Mon 19 Oct | Tue 20 Oct | Wed 21 Oct | Thu 22 Oct | Fri 23 Oct
Install the current macOS build on a clean or test Mac using only the written instructions. | Test writing, quit and reopen, force-quit recovery, snapshot, restore, and vault relocation. | Test native ZIP, DOCX, PDF, and map PNG saves from the packaged Mac app. | Run the guided Local Mode, lapse, web edit, renewal, and merge-conflict scenario. | Approve Mac install and disclosure instructions after a clean-machine pass.
Week 5 · 2026-10-26 to 2026-10-30 · Desktop and project types
Mon 26 Oct | Tue 27 Oct | Wed 28 Oct | Thu 29 Oct | Fri 30 Oct
Arrange or perform the clean Windows install using the written SmartScreen steps. | Confirm the download page shows correct files and unsigned-app disclosure to an entitled account. | Test Novella and Short Story create, write, default-sections, and export flows. | Test D&D and TTRPG prep and recap, Character Builder, map sections, and export. | Test Novel and Comic workflows and approve the six-type evidence matrix.
Week 6 · 2026-11-02 to 2026-11-06 · Product acceptance
Mon 2 Nov | Tue 3 Nov | Wed 4 Nov | Thu 5 Nov | Fri 6 Nov
Test the rebuilt Map Builder using the owner acceptance checklist. | Perform one realistic large-project session across every core workspace. | Test each AI provider you intend to advertise; remove any provider you cannot verify. | Perform the guided phone, tablet, desktop, and accessibility pass. | Approve the feature-completeness report or remove an unready promise from launch.
Week 7 · 2026-11-09 to 2026-11-13 · Legal and release candidate
Mon 9 Nov | Tue 10 Nov | Wed 11 Nov | Thu 12 Nov | Fri 13 Nov
Read Pricing, FAQ, Terms, Privacy, cancellation, storage, Local Mode, Founder, AI, and export copy as a customer. | Approve final copy and business identity and contact details. | Work through the guided Stripe test-mode checklist one dashboard step at a time. | Approve beta-graduation email, launch announcement, pricing message, screenshots, and support template. | Hold the formal go or no-go review and say go only if every hard gate has evidence.
Week 8 · 2026-11-16 to 2026-11-20 · Marketing runway 1
Mon 16 Nov | Tue 17 Nov | Wed 18 Nov | Thu 19 Nov | Fri 20 Nov
If go, approve closing new Beta enrollment and removing Beta from public plan choices. | Email existing Beta testers with launch timing, retained access, notice path, and backup steps. | Publish the 30 November launch announcement and updated marketing pages. | Test the signed-out visitor journey on phone and desktop. | Review interest, tester replies, support load, and analytics; approve copy-only corrections.
Week 9 · 2026-11-23 to 2026-11-27 · Marketing runway 2
Mon 23 Nov | Tue 24 Nov | Wed 25 Nov | Thu 26 Nov | Fri 27 Nov
Publish the main use-case story and demonstrate one complete writer workflow. | Publish the ownership, export, Local Mode, and desktop message. | Publish project-type examples and confirm all six are described honestly. | Review the support runbook, refunds, cancellation, incident contacts, and rollback triggers. | Perform the final guided purchase rehearsal and sign the launch checklist.
Week 10 · 2026-11-30 to 2026-11-30 · Launch
Mon 30 Nov
Approve the production checkout switch, announce launch, and monitor transactions and support.